## Sheet1
Time Savings (Months)
Project | Town / County | Public Need for Hyperbuild | Scoping | Design | Const. | Total Time Saving | Proj. Completion Traditional / Hyperbuild | Const. Award Amount Traditional/Hyperbuild (Millions) | Design Savings (Millions) | Road User Cost Savings*** | Total Cost Savings (Millions)
Route 46 Overpeck Creek Bridge | Ridgefield Park Village, Ridgefield Boro / Bergen | Deficient Bridge / High Volume / Heavy Congestion | 0 | 32 | 16 | 48 | Dec 09 / Nov 05 | $14 / $9.4 | 1.6 | 5.5 | 11.7
Route 1 Olden/Mulberry Street, Superstructure Replacement | Trenton City / Mercer | Deficient Bridge / Heavy Commuter Volumes | 0 | 14 | 8 | 22 | Mar 08 /Nov 05 | $3.0 / $2.7 | 1 | 0.75 | 2.05
Route 179 Alexauken Creek Bridge | West Amwell / Hunterdon | Deficient Bridge | 0 | 12 | 9 | 21 | Aug 07 / Dec 05 | $1.8 / $1.0 | 0.2 | N/A | 1
Route 168 Bellmawr Drainage | Bellmawr Boro / Camden | Severe Flooding / Safety | 0 | 12 | 0 | 12 | Nov 06 / Nov 05 | $4.0 / $4.0 | N/A | 1 | 1
Route 52 Causeway Replacement | Somers Point City, Ocean City / Atlantic, Cape May | Deficient Bridge / Evacuation and Hospital Route | 0 | 0 | 52 | 52 | Apr 2013 / Dec 09 | $300 / $280 | N/A | 5 | 25
Route 9 Bus Shoulder and Pedestrian Improvements | Old Bridge Township / Middlesex | Heavy Commuter Volumes | 0 | 15 | 1 | 16 | Apr 08 / Dec 06 | $8.0 / $7.5 | 0.5 | 0.2 | 1.2
Garden State Parkway and Route 280 (Interchange 145) | East Orange City / Essex | Safety / EZ Pass / Heavy Congestion | 15 | 13 | 8 | 36 | Sep 2010 / Sep 07 | $11.3 / $10.5 | 0.3 | 10 | 11.1
Route 94 Sand Hill Road Intersection Improvements | Vernon Township / Sussex | Economic Development | 0 | 21 | 3 | 24 | Jun 09 / Oct 06 | $4.5 / $3.5 | 0.5 | 0.2 | 1.7
Route 280 Stickel Bridge | Harrison Town, Newark City / Hudson, Essex | Deficient Bridge / High Volume / Heavy Congestion / Staging | 27 | 17 | 36 | 80 | Mar 2014 / Apr 07 | $300 / $20.3 | 26.4 | N/A | 306.01
Route 295 Tomlin Station Road to Route 45 Pavement Rehabilitation | Greenwich Township, West Deptford Township, Paulsboro Borough /Gloucester | Safety / High Volume / Heavy Congestion | 0 | 18 | 12 | 30 | Jan 2010 / Jul 07 | $32 / $25.6 | 0.3 | 4.7 | 11.4
Route 38, Pedestrian Bridge Cherry Hill Mall | Cherry Hill Twp / Camden County | Safety | 17 | 5 | 9 | 31 | Jul 09 / Jun 06 | $3.5 / $2.5 | 0.7 | N/A | 1.7
I-78 Union / Essex Pavement Rehabilitation | Hillside Twip, Union Twp, Newark City, Irvington Twp / Union, Essex | Economic Development/ Safety / High Volume / Heavy Congestion | 12 | 15 | 31 | 58 | Dec 2012 / Dec 07 | $100+ / $40 | 7.3 | 6.3 | 73.6
Route 27 | Franklin Twp / Somerset, North Brunswick, New Brunswick / Middlesex | Safety / High Volume / Heavy Congestion | 18 | 11 | 12 | 41 | Dec 2012 / Jul 09 | $20 / $7 | 0.5 | 7.3 | 20.8
Route I-295; I-76; Route 42 Interchange | Bellmawr Twp / Camden | Safety / High Volume / Heavy Congestion | 36 | 6 | 18 | 60 | Dec 2015 / Dec 2012 | $300 / $250 | 0.5 | $100+ | 150.5
Route 42, College Drive (CR 673) aka Little Grenloch Road | Gloucester Township / Camden | Heavy Congestion / Economic Development | 48 | 0 | 0 | 48 | March 2014 / March 2010 | $20 / $15 | 3 | 2 | 10
TOTALS |  |  | 173 | 191 | 215 | 579 |  |  |  |  | 628.76
***Road User Costs are calculated using a nationally utilized formula that factorthe value of people's time and vehicle operating costs. Road user costs increase when construction activity causes vehicles to either slow down, stop, or take alternate routes.
The actual road user cost varies depending on the amount of delay and the number of vehicles on the road involved.