Classification No. 1  New Construction

CONTINGENCIES & ESCALATION

|  | X | X | = |
| --- | --- | --- | --- |
| Project Total | (1+ C) Contingencies | 1 + [0.01 (Y+1) (Y-2)] Y = Number of Years until midpoint of construction duration. If midpoint is less than 2 years no escalation is required. Maximum value = 10%. | Construction Estimate for PD |

| Project Cost(Mil.) | Contingencies (C) Percent | Average Construction Duration in Years |
| --- | --- | --- |
| 0-10 | 3% | 1 |
| 10-20 | 2.5% | 2 |
| 20-50 | 2% | 3 |
| Over 50 | 1.5% | 4 |

| CONSTRUCTION ENGINEERING (CE) |  |
| --- | --- |

| Project Cost (Mil.) | % of Construction Cost |
| --- | --- |
| Less than 1.0 | 28.4% |
| 1.0 to 5.0 | 17.6% |
| 5.0 to 10.0 | 12.2% |
| 10.0 & above | 9.5% |
| CONSTRUCTION ENGINEERING AMOUNT |  |

###### CONTINGENCIES FOR CONSTRUCTION CHANGE ORDER

| Total Federal Participating Items in Millions of $ | Construction Change Order Contingency Amount |
| --- | --- |
| $0 to 0.1 | $6,000 |
| 0.1 to 0.5 | 25,000 |
| 0.5 to 5.0 | 25,000 + 4% of amount in excess of $500,000 |
| 5.0 to 10.0 | 205,000 + 3% of amount in excess of $5,000,000 |
| 10.0 to 15.0 | 355,000 + 2% of amount in excess of $10,000,000 |
| 15.0 and Above | 500,000 |

| For State Funded Projects, Contingencies for Change orders = 0 |  |
| --- | --- |
| CHANGE ORDER CONTINGENCIES | = |

Class. No. 2 - RECONSTRUCTION, WIDENING & DUALIZATION

CONTINGENCIES & ESCALATION

|  | X | X | = |
| --- | --- | --- | --- |
| Project Total | (1+ C) Contingencies | 1 + [0.01 (Y+1) (Y-2)] Y = Number of Years until midpoint of construction duration. If midpoint is less than 2 years no escalation is required. | Construction Cost for PD Estimate |

| Project Cost(Mil.) | Contingencies (C) Percent | Average Construction Duration in Years |  |
| --- | --- | --- | --- |
| 0-5 | 3% | 1 |  |
| 5-20 | 2.5% | 2 |  |
| Over 20 | 2% | 3 |  |
| ROW COST If there is no ROW cost on the project indicate “No ROW” in the box |  |  |  |

| CONSTRUCTION ENGINEERING (CE) |  |
| --- | --- |

| Project Cost (Mil.) | % of Construction Cost |
| --- | --- |
| Less than 1.0 | 31.1% |
| 1.0 to 5.0 | 20.3% |
| 5.0 to 10.0 | 16.2% |
| 10.0 & above | 12.2% |
| CONSTRUCTION ENGINEERING AMOUNT |  |

###### CONTINGENCIES FOR CONSTRUCTION CHANGE ORDER

| Total Federal Participating Items in Millions of $ | Construction Change Order Contingency Amount |
| --- | --- |
| $0 to 0.1 | $6,000 |
| 0.1 to 0.5 | 25,000 |
| 0.5 to 5.0 | 25,000 + 4% of amount in excess of $500,000 |
| 5.0 to 10.0 | 205,000 + 3% of amount in excess of $5,000,000 |
| 10.0 to 15.0 | 355,000 + 2% of amount in excess of $10,000,000 |
| 15.0 and Above | 500,000 |

| For State Funded Projects, Contingencies for Change orders = 0 |  |
| --- | --- |
| CONTINGENCIES | = |

Classification No. 3 - WIDENING & RESURFACING

CONTINGENCIES & ESCALATION

|  | X | X | = |
| --- | --- | --- | --- |
| Project Total | (1+ C) Contingencies | 1 + [0.01 (Y+1) (Y-2)] Y = Number of Years until midpoint of construction duration. If midpoint is less than 2 years no escalation is required. | Construction Cost for PD Estimate |

| Project Cost(Mil.) | Contingencies (C) Percent | Average Construction Duration in Years |
| --- | --- | --- |
| 0-10 | 3% | 1 |
| Over 10 | 2.5% | 2 |

| CONSTRUCTION ENGINEERING (CE) |  |
| --- | --- |

| Project Cost (Mil.) | % of Construction Cost |
| --- | --- |
| Less than 1.0 | 27.0% |
| 1.0 to 5.0 | 14.9% |
| 5.0 to 10.0 | 13.5% |
| 10.0 & above | 12.2% |
| CONSTRUCTION ENGINEERING AMOUNT |  |

###### CONTINGENCIES FOR CONSTRUCTION CHANGE ORDER

| Total Federal Participating Items in Millions of $ | Construction Change Order Contingency Amount |
| --- | --- |
| $0 to 0.1 | $6,000 |
| 0.1 to 0.5 | 25,000 |
| 0.5 to 5.0 | 25,000 + 4% of amount in excess of $500,000 |
| 5.0 to 10.0 | 205,000 + 3% of amount in excess of $5,000,000 |
| 10.0 to 15.0 | 355,000 + 2% of amount in excess of $10,000,000 |
| 15.0 and Above | 500,000 |

| For State Funded Projects, Contingencies for Change orders = 0 |  |
| --- | --- |
| CONTINGENCIES | = |

Classification No. 4 - RESURFACING

CONTINGENCIES & ESCALATION

|  | X | X | = |
| --- | --- | --- | --- |
| Project Total | (1+ C) Contingencies | 1 + [0.01 (Y+1) (Y-2)] Y = Number of Years until midpoint of construction duration. If midpoint is less than 2 years no escalation is required. | Construction Cost for PD Estimate |

| Project Cost(Mil.) | Contingencies (C) Percent |  | Average Construction Duration in Years |
| --- | --- | --- | --- |
| 0-20 | 3% |  | 1 |
| Over 20 | 2% |  | 2 |
| CONSTRUCTION ENGINEERING AMOUNT |  |  |  |

| CONSTRUCTION ENGINEERING (CE) |  |
| --- | --- |

| Project Cost (Mil.) | % of Construction Cost |
| --- | --- |
| Less than 1.0 | 20.3% |
| 1.0 to 5.0 | 14.9% |
| 5.0 to 10.0 | 10.8% |
| 10.0 & above | 9.5% |

###### CONTINGENCIES FOR CONSTRUCTION CHANGE ORDER

| Total Federal Participating Items in Millions of $ | Construction Change Order Contingency Amount |
| --- | --- |
| $0 to 0.1 | $6,000 |
| 0.1 to 0.5 | 25,000 |
| 0.5 to 5.0 | 25,000 + 4% of amount in excess of $500,000 |
| 5.0 to 10.0 | 205,000 + 3% of amount in excess of $5,000,000 |
| 10.0 to 15.0 | 355,000 + 2% of amount in excess of $10,000,000 |
| 15.0 and Above | 500,000 |

| For State Funded Projects, Contingencies for Change orders = 0 |  |
| --- | --- |
| CONTINGENCIES | = |

Classification No. 5- BRIDGE REPAIR

CONTINGENCIES & ESCALATION

|  | X | X | = |
| --- | --- | --- | --- |
| Project Total | (1+ C) Contingencies | 1 + [0.01 (Y+1) (Y-2)] Y = Number of Years until midpoint of construction duration. If midpoint is less than 2 years no escalation is required. | Construction Cost for PD Estimate |

| Project Cost(Mil.) | Contingencies (C) Percent | Average Construction Duration in Years |
| --- | --- | --- |
| 0-5 | 3% | 1 |
| Over 5 | 2.5% | 2 |

| CONSTRUCTION ENGINEERING (CE) |  |
| --- | --- |

| Project Cost (Mil.) | % of Construction Cost |
| --- | --- |
| Less than 1.0 | 14.9% |
| 1.0 to 5.0 | 12.2% |
| 5.0 to 10.0 | 10.8% |
| 10.0 & above | 9.5% |
| CONSTRUCTION ENGINEERING AMOUNT |  |

###### CONTINGENCIES FOR CONSTRUCTION CHANGE ORDER

| Total Federal Participating Items in Millions of $ | Construction Change Order Contingency Amount |
| --- | --- |
| $0 to 0.1 | $6,000 |
| 0.1 to 0.5 | 25,000 |
| 0.5 to 5.0 | 25,000 + 4% of amount in excess of $500,000 |
| 5.0 to 10.0 | 205,000 + 3% of amount in excess of $5,000,000 |
| 10.0 to 15.0 | 355,000 + 2% of amount in excess of $10,000,000 |
| 15.0 and Above | 500,000 |

| For State Funded Projects, Contingencies for Change orders = 0 |  |
| --- | --- |
| CONTINGENCIES | = |

Classification No. 6 - INTERSECTION IMPROVEMENT

CONTINGENCIES & ESCALATION

|  | X | X | = |
| --- | --- | --- | --- |
| Project Total | (1+ C) Contingencies | 1 + [0.01 (Y+1) (Y-2)] Y = Number of Years until midpoint of construction duration. If midpoint is less than 2 years no escalation is required. | Construction Cost for PD Estimate |

| Project Cost(Mil.) | Contingencies (C) Percent | Average Construction Duration in Years |
| --- | --- | --- |
| 0-5 | 3% | 1 |
| Over 5 | 2.5% | 2 |

| CONSTRUCTION ENGINEERING (CE) |  |
| --- | --- |

| Project Cost (Mil.) | % of Construction Cost |
| --- | --- |
| Less than 1.0 | 36.5% |
| 1.0 to 5.0 | 35.1% |
| 5.0 to 10.0 | 12.2% |
| 10.0 & above | 10.5% |
| CONSTRUCTION ENGINEERING AMOUNT |  |

###### CONTINGENCIES FOR CONSTRUCTION CHANGE ORDER

| Total Federal Participating Items in Millions of $ | Construction Change Order Contingency Amount |
| --- | --- |
| $0 to 0.1 | $6,000 |
| 0.1 to 0.5 | 25,000 |
| 0.5 to 5.0 | 25,000 + 4% of amount in excess of $500,000 |
| 5.0 to 10.0 | 205,000 + 3% of amount in excess of $5,000,000 |
| 10.0 to 15.0 | 355,000 + 2% of amount in excess of $10,000,000 |
| 15.0 and Above | 500,000 |

| For State Funded Projects, Contingencies for Change orders = 0 |  |
| --- | --- |
| CONTINGENCIES | = |

Classification No. 7 - SAFETY & TRAFFIC CONTROL

CONTINGENCIES & ESCALATION

|  | X | X | = |
| --- | --- | --- | --- |
| Project Total | (1+ C) Contingencies | 1 + [0.01 (Y+1) (Y-2)] Y = Number of Years until midpoint of construction duration. If midpoint is less than 2 years no escalation is required. | Construction Cost for PD Estimate |

| Project Cost(Mil.) | Contingencies (C) Percent | Average Construction Duration in Years |
| --- | --- | --- |
| 0-5 | 3% | 1 |
| Over 5 | 2.5% | 2 |

| CONSTRUCTION ENGINEERING (CE) |  |
| --- | --- |

| Project Cost (Mil.) | % of Construction Cost |
| --- | --- |
| Less than 1.0 | 21.6% |
| 1.0 to 5.0 | 12.2% |
| 5.0 to 10.0 | 12.2% |
| 10.0 & above | 12.2% |
| CONSTRUCTION ENGINEERING AMOUNT |  |

###### CONTINGENCIES FOR CONSTRUCTION CHANGE ORDER

| Total Federal Participating Items in Millions of $ | Construction Change Order Contingency Amount |
| --- | --- |
| $0 to 0.1 | $6,000 |
| 0.1 to 0.5 | 25,000 |
| 0.5 to 5.0 | 25,000 + 4% of amount in excess of $500,000 |
| 5.0 to 10.0 | 205,000 + 3% of amount in excess of $5,000,000 |
| 10.0 to 15.0 | 355,000 + 2% of amount in excess of $10,000,000 |
| 15.0 and Above | 500,000 |

| For State Funded Projects, Contingencies for Change orders = 0 |  |
| --- | --- |
| CONTINGENCIES | = |

For Classification 8 thru 13 the Designer should choose the most similar Classification from 1 thru 7 as defined in Appendix C and use the appropriate calculations.